## Read Me
S Y S T E M S E N G I N E E R I N G
§ | DESKBOOK
VERIFICATION MATRIX · WORKING TEMPLATE · VCRM → VRTM / RVTM
Build the VCRM, grow it into a VRTM / RVTM.
Fill one row per requirement-verification line on the VRTM tab. The Coverage Roll-Up tab recomputes live. Structure adapted from FAA VVSPT-E5-GDE-017 (public) and mapped to DoD T&E terminology.
01 VERIFICATION METHODS · WHAT EACH ONE PROVES
| Code | Method | What it proves (evidence) | Use when
| T | Test | Systematically exercise the item and record quantitative data; accept by comparing data to pre-set criteria. | A measured number must be captured and judged against a threshold.
| A | Analysis | Models, simulation, equations, or similarity to a qualified item; calculated or representative data. | Test is impractical or premature, or the condition can't be created.
| I | Inspection | Visual / dimensional exam of the item or its documentation against a standard — no lab instrumentation. | Confirming a physical feature, marking, workmanship, or a certificate of compliance.
| D | Demonstration | Operate under a defined scenario and observe pass / fail; only observational data is recorded. | Qualitative functional behavior — 'it worked' is the bar, no number captured.
Test vs Demonstration: recorded quantitative data vs observation only. 'By similarity' is an Analysis argument — cite the qualified item. A Certificate of Compliance is an Inspection.
02 ONE MATRIX, THREE NAMES · KNOW THE SCOPE
| A TRUE VCRM (the minimum) |  | A VRTM / RVTM (the VCRM, extended)
| • Requirement ID |  | + …plus Parent / source trace
| • Requirement text |  | + …plus Activity & Test-Case ID
| • Method (T / A / I / D) |  | + …plus Success criteria
| • Verification level |  | + …plus Run date & Result
| • T&E phase (optional) |  | + …plus Verification status
Same backbone, different ambition. The VCRM answers HOW each requirement is verified; the VRTM / RVTM also answers WHETHER — and where the proof lives. FAA calls it a VRTM; industry also says RVTM. Don't call a half-built RVTM a VCRM.
| 03 CRITICALITY (DoD) |  | 04 RESULT VOCAB
| KPP | Key Performance Parameter — must-meet; failure can end the program. | Pass | Criteria met; evidence on file.
| KSA | Key System Attribute — important, below KPP. | Fail | Run and did not meet criteria.
| CTP | Critical Technical Parameter — DT&E engineering measure. | Partial | Some criteria met / some events incomplete.
| N/A | Not a critical requirement. | Deferred | Moved out of scope — excluded from completion denominator.
|  |  | Untested | Not yet run.
COI result is reported Yes / No / Limited.
05 MEASURES (OT&E) · COI → MOE / MOS → MOP
COI (Critical Operational Issue) → MOE / MOS (effectiveness / suitability) → MOP (measurable performance). DT&E verifies CTPs and the ability to meet KPPs / KSAs; OT&E assesses COIs by tracing test cases to MOPs.
06 HOW TO USE
| 1 | One row per requirement-verification LINE. A requirement verified by several methods or phases occupies several rows — repeat the Req ID.
| 2 | Pick a Method code (T/A/I/D); the full name fills in automatically.
| 3 | Flag criticality (KPP/KSA/CTP/N/A) and set the T&E phase and activity.
| 4 | Write verifiable success criteria — bind a number to a condition.
| 5 | Record Test-Case ID, responsible org, evidence reference, run date, and Result.
| 6 | Read the Coverage Roll-Up — it counts verification lines and updates live.
07 WRITING VERIFIABLE SUCCESS CRITERIA
| Bad |  | Good
| ✗ “low latency” |  | ✓ “≤ 2.0 s glass-to-glass, nominal link”
| ✗ compound shall-statement |  | ✓ split, then one row each
| ✗ Inspection for a perf threshold |  | ✓ Test for a measured value
| ✗ “as required” |  | ✓ explicit limit + tolerance
§ | Teaching systems engineers the tools that matter.

## VRTM
S Y S T E M S E N G I N E E R I N G
§ | DESKBOOK
VRTM · VERIFICATION REQUIREMENTS TRACEABILITY MATRIX (DoD-adapted)
Methods: T Test · A Analysis · I Inspection · D Demonstration. One row per verification line (repeat the Req ID for multiple methods/phases). Highlighted Method cell = requirement present but no method assigned (orphan).
Req ID | Requirement (text) | Parent / Source Trace | Criticality (KPP/KSA/CTP) | Method | Method (name) | Verification Level | T&E Phase | Activity / Event | Test Case / Proc ID | Success Criteria (verifiable) | Responsible (org / facility) | Evidence / Results Ref | Run Date | Result | Notes
SR-2 | Provide EO/IR imagery to the MCE; end-to-end latency ≤ 2 s. | CDD KPP-2 | KPP | T | Test | System | DT&E | SAT | TC-014 | Glass-to-glass latency ≤ 2.0 s over 10 trials, nominal link. | Gov SIL | VR-014 | 2026-02-10 | Pass
SR-12 | Endurance ≥ 10 h on station at full payload. | CDD KPP-3 | KPP | T | Test | System | DT&E | Flight Test | TC-022 | Measured endurance ≥ 10.0 h, full payload, ISA. | Range Flt Test | VR-022 | 2026-01-22 | Fail | Achieved 8.7 h; CR open.
SR-15 | With an airborne relay, operate ≥ 250 km. | SR-14 | N/A | A | Analysis | System | DT&E | Analysis | AR-008 | Link-budget analysis ≥ 250 km with relay, ≥ 10 dB margin. | SE Analysis | VR-008 | 2026-03-05 | Pass | Relay flight deferred; analysis credited.
SR-21 | Exterior markings and data plate present and legible. | SRD-9 | N/A | I | Inspection | Component | DT&E | QA Inspection | QI-105 | Markings / data plate comply with MIL-STD-130N. | QA | VR-105 | 2026-02-28 | Pass
SR-25 | Operator executes automated launch sequence from the GCS. | CDD KSA-1 | KSA | D | Demonstration | System | OT&E | IOT&E | TC-040 | Automated launch sequence completes with no faults. | OTA |  |  | Partial | 1 of 3 OT events incomplete.
SR-30 | Implement cybersecurity controls per the RMF baseline. | DoDI 8510.01 | N/A |  |  | System | [7 empty] | Untested | ORPHAN — method not yet assigned.
SR-40 | Provide a secondary SATCOM datalink. | CDD KSA-2 | KSA | T | Test | Subsystem | DT&E | FAT | TC-045 | SATCOM link established and maintained ≥ 30 min. | Vendor | VR-045 | 2026-02-15 | Pass | DT line (same req, see OT line below).
SR-40 | Provide a secondary SATCOM datalink. | CDD KSA-2 | KSA | D | Demonstration | Subsystem | OT&E | IOT&E | TC-061 | Operator establishes SATCOM link in the field. | OTA |  |  | Untested | OT line — second verification of the same requirement.
Note on D5: KPP / KSA / CTP / N/A (dropdown). The DoD criticality flag (replaces FAA's CPR).
Note on E5: Enter T, A, I, or D (dropdown).
Note on K5: Bind a number to a condition; state the pass/fail boundary explicitly.
Note on O5: Pass / Fail / Partial / Deferred / Untested. Deferred is excluded from the completion denominator.

## Coverage Roll-Up
S Y S T E M S E N G I N E E R I N G
§ | DESKBOOK
COVERAGE ROLL-UP · LIVE FROM THE VRTM TAB
01 PLANNING COVERAGE
| Verification lines (rows) | 8
| Distinct requirements | 7 |  | A requirement may span several lines.
| Method assigned | 7
| Unassigned (orphans) | 1
| Method coverage | 87.5% |  | Share of lines with a method assigned — NOT verification done.
02 METHOD MIX
| Test (T) | 3
| Analysis (A) | 1
| Inspection (I) | 1
| Demonstration (D) | 2
| Check — sum = assigned | 7 |  | Should equal Method assigned.
03 VERIFICATION RESULT
| Pass | 4
| Fail | 1
| Partial | 1
| Deferred | 0
| Untested | 2
| Verification complete | 50% |  | Pass ÷ (lines − Deferred). NOT the same as method coverage.
| Pass of all lines | 50% |  | Pass ÷ all lines.
04 COVERAGE BY CRITICALITY
| Flag | Lines | Passed | % complete
| KPP | 2 | 1 | 50%
| KSA | 3 | 1 | 33.33%
| CTP | 0 | 0 | 0%
Use this to answer: are all KPPs verified?
05 COVERAGE BY T&E PHASE
| Phase | Lines | Passed | % complete
| DT&E | 5 | 4 | 80%
| OT&E | 2 | 0 | 0%
| LFT&E | 0 | 0 | 0%
06 COVERAGE BY LEVEL
| Level | Lines | Passed | % complete
| System | 5 | 2 | 40%
| Subsystem | 2 | 1 | 50%
| Component | 1 | 1 | 100%
§ | Teaching systems engineers the tools that matter.